Strategic Plan for the NJ CHWI: 8-22-06

|  | Action steps and strategies | Key partners/delegation | Action to be Complete by (date) |
| --- | --- | --- | --- |
| Outcomes to be completed by 8/31/08: |  |  |  |
| All HRSA Objectives Met | See separate outline at end |  |  |
| Long term Money is Secured for CHWI | -State Appropriations Case Statement on Cost effectiveness Literature Reviews Convene a possible Legislative Briefing -Solicit Contributions from: NJHA, NJPCA, UMDNJ, NJ Health Department | Elyse Perweiler, Roz Council, Parvin Ahmadkhanlou NJHA, NJPCA, UMDNJ, NJ Health Department | Carl –Lit reviews by end of Sept 2006 Legislative briefing Jan or Feb 2007 |
| NJ State CHW Network established | -Attend Cluster Meetings: NJ PCA agreed to promote the cluster concept to their CHW group meetings. Meet by the end of October -Application for funding to Kellogg: -Preliminary Proposal -Call to Kellogg funding officer | Bernice W, Dwyan M., Crystal, Leslie M. Jackie Scott( CSHO), Barbara Sabol | Cluster Meetings: All Met by Dec. 1 2006 Submit Proposal By August 31, 2006 |
| Conduct NJ State CHW Workforce Study | -Run Table SPSS tables on Inventory Data: 1.Send Carl SPSS Download 2.Carl to work on joint report to talk about the workforce 3.Need to obtain data from NJ PCA, HA, CSHO -Grant monies to do a thorough research for NJ | Carl R., Carolyn Brae, Mary DiTri, Leslie M. Parvin A, Kathy | Carl to complete data tables by Sept 15, 2006 Grant Monies for research June 2007 |
| NJ CHW Identity Campaign | -Stakeholder agreement to a common message that will support the work of CHWs: Press release Website Newsletter Pharmaceutical/Physician Sponsored Poster to include supporters’ organ. name -Proclamation from the State -Identify other stakeholders; presentations to new groups: NJ Home Health Aides Association Social Work | NJSPHE, NJHA, NJSNA, UMDNJ (John Crosby, Jerry Carey), CHW Clusters, Local News Paper, Camden AHEC Reporter(Shawn Rea) Arlen M., Ilse Z. Dwyan | Convene Stakeholder Meeting: end of January 2007 Present to new Stakeholders: End of Sept 2006 |
| Annual Conference | -1 Day Conference: 1. Sponsorship 2. Planning 3. Location 4. Date; “Save the Date” Postcards 5. Theme/ Conference Focus -Conference call with Conference Planning Committee -Strategic Planning for CHW Conference in 2008 | Shelly C.- Logistics, Crystal B.- Help with Sponsors, Conference Planning Committee, Attendee Mailing List | Conference to be held March 2007 Schedule Conference all w/ Planning Comm. Week of Sept. 17 |
| NJ State CHW Job Description | -Draft sent to Advisory Council Members -Need to come up with next Steps for submitting the Labor Department -Development formal adoption in Oct. during next Advisory council meeting | Kathy R. | October 2006 |
| CHWI Website/ Newsletter | -Develop a Template -Develop content for web based newsletter - solicit volunteers to work on newsletter | Valerie, Dwyan, CHW Cluster | Jan/Feb 2007 |
| NJ State Standards and Credentials | -Send Core Competency to Employers Email List -Feedback from CHWs during Cluster Meetings - Build a Case on Credentialing - Implementation of Standard for State -Convene Standards and Credentialing Committee | CSHO Jackie Scott Cluster Meetings Standard and Credentialing Comm. | Email Core Comp First week in September 2006 Cluster Meetings: By Sept/Oct. 2006 State Stand. Dec. 2007 Convene Comm. by end of Sept 2006 |
| Basic Statewide Curriculum in place | -Revising CHW Curriculum: AHEC Invite persons to be apart of a Curriculum review committee: Revise , Review and Pilot Revise as it relates to the Core Competencies - Collect all Material | Bernice W., Martha C., (AHEC) Bernadette West ( UMDNJ) School of Public Health Robin Eubanks Chair Curriculum Committee?? | Contact Sep 06 Convene Committee Revision May 07 |
| CE series | -Implement Workshop Series: - Black Infant Mortality: Preterm Labor - Epilepsy- Epilepsy Foundation -Disaster Preparedness Define Educational Needs: Open Enrollment for CHWs Contact Employers regarding training needs for CHWS | Leslie M., Pat, Drew, Leslie Leslie (BIMR) CHW Cluster | Complete workshops no later than Dec. 01 Work with Cluster meetings and survey employers from Jan –April 2007 |
| Supervising and Managing CHWS | - Meeting and presenting to Nurses, Social workers and Health educators -Develop presentation into one day workshop: - Search for funding to support a one day workshop | NJSNA, NJSOPHE, CHEC | To be completed by Jan. or Feb 2007 Offer Workshop July 2007 |
| CHW Regional Leadership Retreat | -Research other leadership retreat Models -Mid Atlantic Health Leadership Retreat (JHU) - Regional meeting in New Jersey 05 - Meet with NJ and other state CHW leaders to discuss types of topics they would like to see being discussed at the retreat Skill building and technical development Secure funding: Kellogg | Dwyan and Carl CHW Cluster Leaders | Jan 2007 March 2007 Convene Regional Retreat Fall 2008 |