| HRSA Objectives: Outcomes to be completed by 8/31/08: | Action steps and strategies | Key partners/delegation | Action to be Complete by (date) |
| --- | --- | --- | --- |
| I.1.1: at least 50 medical residents will have participated (or be participating) in residency sites in New Jersey working in structured settings alongside CHWs | - Research Medical Residency programs: -Primary Care -Obstetrics -Family Medicine -Pediatrics -Internal Meds -Medical Oncology - Develop an Action Plan | Carl W., Elyse P. State Council on Teaching Hospitals | End of Nov. 2006 |
| I.1.2: at least 300 medical and other health professions students will have completed or be participating in assignments working in teams with CHWs | -Community Service Rotation -COPC Project Obtain contact with other Med School Campuses Newark New Brunswick -Contact School of Nursing | Dr. Paul Krueger, Elyse Perweiler, Gladys Valdiviseo Claudia Switala Ana Natala Parear | Develop Contacts no later than Dec 2006 Reach goal by Aug 2008 |
| I.2.1: at least six new health care delivery initiatives (pilot projects) funded from other sources | -NCOA -Health Disparities - Publicize research- Role of CHW | Elyse Perweiler Diane Brown( IHED) | End of Sept 2006 |
| I.2.2: at least three journal articles or conference presentations by major employers (e.g., FQHCs) on the impact of CHWs in healthcare delivery | - Possible present about the CHW role with the new health initiative with Institute on Successful Aging - Possible article, abstract or report (paper) from employers of CHWS and the work they do. Publish some outcomes/analysis. | Elyse Perweiler NCOA | Begin Process October 2006 |
| I.3.1: curriculum modules will be implemented in at least four medical and other university-level health professions education programs on skills needed to work effectively with CHWs, and at least 800 students will receive these modules | - School of Med.- New Curriculum 1. Learning objectives 2. Developing Cases -Get curriculum structure -Get curriculum material | Dr. Paul Krueger | Response for Learning objectives: early Oct. 2006 Obtain Material: May 2007 Implement August 2007 |
| I.3.2: at least three CHWs working as guest lecturers in training for health professionals, out of ten CHWs trained and prepared, and at least 1,000 students will receive instruction from them | - CHW instructor consultant on board to help develop curriculum and help with preparing a CHW to become and instructor with the UMDNJ -Call Consultant to meet to sign agreement form - Review Consultant curriculum - Consultant to meet faculty - Recruitment of CHWs from the cluster for training and preparation for med school CHW instructor - instructor in med school curriculum | Gladys Valdivieso CHW Clusters | Sept 1. 2006 set up meeting to sign contract Consultant Faculty meeting Oct. 2006 First half of 2007 to recruit August 2007 Instructor begins |
| II.1. career pathways and supports for CHWs to enter other health related professions. By 9/08: II.1.1. at least 70 CHWs will enter other training. II.1.2. at least 50 CHWs will either complete or remain enrolled | -Schedule meeting with Career development taskforce: 1. develop and action plan 2. Host 2 regional meetings: one at 9am and one meeting at 2:pm Develop a plan for: Career in place: meeting in Southern NJ Career advancement in related fields: Northern NJ | Career Development Taskforce: | Schedule meetings for Sept 14 |