## Sheet1
SIM CHW Initiative Workplan 2019
Focus Area | Activity | Detailed Activity | Deliverable | Quarter | Dates | Update for SIM PO call with Steph and Chris 9.24.2019
Stakeholder Engagement, Education and Community Integration | Statewide Outreach, Engagement and Support for passage of legislation for CHW Certification. | Implement work plan to continue providing support in the education of CHW certification. Including collaborating with Health Equity Solutions, Hispanic Health Council and others to build capacity and advocacy strategies. | Legislation for CHW Certification is passed in the 2019 Legislative session | Q1 – Q2 | 2/1/2019 – 7/31/2019 | Completed. All materials developed for marketing have been provided to HES via shared drive.
| CHW Website is marketed widely and provides CHWs, Employers and Stakeholders with up-to-date information. | Refine the CHW website and update content as needed for CHWs, employers, and other stakeholders. | CHW website is updated with current information on a monthly basis. | Q1 – Q2 Q1 - Q4 | 2/1/2019 – 7/31/2019 1/31/2020 | 99 % Complete - Last review for final "eagle eyes." Need to provide to CMMI for review/Approval per call last week. Can a meeting with Rose be set up this week?
Infrastructure, Sustainability and Development | Support and assistance with the CHW Advisory Committee for the continued development of the CHW workforce in CT. | Research and further develop functions and details in the Report to the Legislature on the Recommendations for Certification of CHWs. | The recommended processes for the CHW Certification Recommendations are ready for implementation. | Q1 – Q4 | 2/1/2019 – 1/31/2020 | Research with other states that have implemented Certification was continued, and updates to previous information are being incorporated into previous information.
|  | Support and assist in defining the roles/processes for the the CHW Association of CT in the Certification process. | The CHW Association of CT's role and strategies for implementing Certification in CT are defined and with funding and staffing. | Q1 – Q2 | 2/1/2019 – 7/31/2019 | Millie Seguinot, President of CHW Association. of CT was included in SIM personnel for part time work in Nov. 2018 with approval from Jenna. This would allow for her to be paid to do CHW Assn work while at SW AHEC, which was a job function change. Shortly after that (November 5th) she informed us that she was having surgery on November 19, 2018, which subsequently got postponed until December 3th. She expected to return Feb. 3, 2019. This got extended twice, and she returned on April 12th. She worked 1 day, and then went to a conference for a week. She returned on April 22nd, and submitted her resignation as of May 3rd, 2 weeks later. While she was out she had another CHWACT Board member participate in meetings, who brought the information back to the Association. Any further steps to implement any models or strategies other than sharing the marketing materials that were created with the Association were unable to be developed due to medical leave.
|  | Continue to inventory existing and proposed CHW sustainability models in other states | Identify feasible models for CHW payment for CT. | Q1 – Q4 | 2/1/2019 – 1/31/2020 | Have checked with other states, and a report is being developed and finalized.
Community Health Worker Workforce Development | Implementation of a CHW Apprenticeship program in CT. | Continue the Implementation and refining of the CHW Apprenticeship program with the CT Department of Labor and workforce agency partners. | CHW Apprenticeship program implemented with at least one employer | Q1 – Q4 | 2/1/2019 – 1/31/2020 | Met with CHN, Project Access, Clifford Beers, Optimus Health Care, and also briefly discussed other agencies. Optimus Health Care agreed to be the 1st employer for CHW Apprenticeship in CT during meeting on April 2nd. Have worked with Optimus staff, HCAP Consultant Anne Wetmore, and developed Apprenticeship Standards for didactic and one the job training. Final forms have been completed, and have several small changed
| CHW Training Programs have a process for obtaining college credits for their courses | Research and develop methods for Core Competency training programs to be eligible for college credits | CHW Training programs have equivalent coursework and a method for awarding college credits is available to all training programs. | Q1 – Q4 | 2/1/2019 – 1/31/2020 | College credits are provided in differing ways, dependent upon the institution or agency. Community Colleges have a process for assigning credits to courses based on the internal process at the college, working with the Academic Dean, the Curriculum Committee, etc. Content courses with credits are preferred to be part of a pathway or certificate program. Outside agencies whom are not educational insitutions may have to work with a college or university to develop a method of working together to obtain college credit. Charter Oak State College may be able to assess the training program/s and provide college credits if deemed appropriate.
| CHW Internship programs have equivalent basic requirements across the state. | Research and develop the basic requirements for CHW Internship programs and have them recognized statewide. | CHW Internships have equivalent educational standards across the CHW Training programs. | Q1 – Q3 | 2/1/2019 – 10/31/2019 | A group individuals representing CHW training programs, CHWs, CHW Association of CT, and CHW Allies were invited to participate in 2 in-person meetings with a consultant facilitator to discuss the development of recommedations for the internship for CHWs as recommended by the Report to the Legislature on CHW Certification and Public Act 19-117. Research with other training programs and their internship structures was completed. The final report with appendices showing existing forms, evaluations and requirements are included.
| Development of the requirements to become a recognized Training Vendor under the Certification for CHWs in CT. | Standards are established for the assessment of CHW training programs to become Training vendors. | CHW Training Vendor Criterion are developed | Q3 | 2/1/2019 - 10/31/2019 | Research of CHW training programs/vendors that have been approved as training vendors in other states (N=6) is being completed. The 6 states that have been researched have an application process for training programs to become vendors that meet the certification program requirements. Examples of the applications to become a training vendor are included. The final report will incluce appendices showing existing forms and processes in each state.
DRAFT